## Product Backlog
| Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. Project Setup (Spring Boot + Maven) Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). Configure Maven dependencies (Web, JPA, Validation, Security). Set up folder structure following clean architecture. Create environment profiles: dev, test, prod. Implement global exception handler (ErrorResponse, ControllerAdvice). | MUST HAVE | Project Setup (Spring Boot + Maven) | Team 1 | 2- In Progress
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. Project Setup (Spring Boot + Maven) Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). Configure Maven dependencies (Web, JPA, Validation, Security). Set up folder structure following clean architecture. Create environment profiles: dev, test, prod. Implement global exception handler (ErrorResponse, ControllerAdvice). | MUST HAVE | Project Setup (Spring Boot + Maven) | Team 1 | 3- Completed
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. Project Setup (Spring Boot + Maven) Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). Configure Maven dependencies (Web, JPA, Validation, Security). Set up folder structure following clean architecture. Create environment profiles: dev, test, prod. Implement global exception handler (ErrorResponse, ControllerAdvice). | MUST HAVE | Project Setup (Spring Boot + Maven) | Team 1 | 3- Completed
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. Project Setup (Spring Boot + Maven) Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). Configure Maven dependencies (Web, JPA, Validation, Security). Set up folder structure following clean architecture. Create environment profiles: dev, test, prod. Implement global exception handler (ErrorResponse, ControllerAdvice). | MUST HAVE | Project Setup (Spring Boot + Maven) | Team 1 | 3- Completed
|  | InternT1 - 005(Haritha p - 3rd ECE) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. Project Setup (Spring Boot + Maven) Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). Configure Maven dependencies (Web, JPA, Validation, Security). Set up folder structure following clean architecture. Create environment profiles: dev, test, prod. Implement global exception handler (ErrorResponse, ControllerAdvice). | MUST HAVE | Project Setup (Spring Boot + Maven) | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---MySQL/PostgreSQL Configuration---- Install/Configure MySQL or PostgreSQL. Create schema: spvms_db. Write initial SQL tables (User, Roles, Vendor, PR, PO). Integrate Flyway/Liquibase for DB migrations. Test DB connection using Spring Boot. | MUST HAVE | MySQL/PostgreSQL Configuration | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---MySQL/PostgreSQL Configuration---- Install/Configure MySQL or PostgreSQL. Create schema: spvms_db. Write initial SQL tables (User, Roles, Vendor, PR, PO). Integrate Flyway/Liquibase for DB migrations. Test DB connection using Spring Boot. | MUST HAVE | MySQL/PostgreSQL Configuration | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---MySQL/PostgreSQL Configuration---- Install/Configure MySQL or PostgreSQL. Create schema: spvms_db. Write initial SQL tables (User, Roles, Vendor, PR, PO). Integrate Flyway/Liquibase for DB migrations. Test DB connection using Spring Boot. | MUST HAVE | MySQL/PostgreSQL Configuration | Team 2 | 3- Completed
|  | InternT2 - 009(Bade Navya - 4th CSE) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---MySQL/PostgreSQL Configuration---- Install/Configure MySQL or PostgreSQL. Create schema: spvms_db. Write initial SQL tables (User, Roles, Vendor, PR, PO). Integrate Flyway/Liquibase for DB migrations. Test DB connection using Spring Boot. | MUST HAVE | MySQL/PostgreSQL Configuration | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---MySQL/PostgreSQL Configuration---- Install/Configure MySQL or PostgreSQL. Create schema: spvms_db. Write initial SQL tables (User, Roles, Vendor, PR, PO). Integrate Flyway/Liquibase for DB migrations. Test DB connection using Spring Boot. | MUST HAVE | MySQL/PostgreSQL Configuration | Team 2 | 3- Completed
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ----JPA/Hibernate Entity Model---- Create entities: User, Role, Vendor, Item, PR, PO. Establish relationships: One-to-Many, Many-to-One. Add JPA validation annotations. Configure ID generation strategies. Test repository queries using CommandLineRunner | MUST HAVE | JPA/Hibernate Entity Model | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ----JPA/Hibernate Entity Model---- Create entities: User, Role, Vendor, Item, PR, PO. Establish relationships: One-to-Many, Many-to-One. Add JPA validation annotations. Configure ID generation strategies. Test repository queries using CommandLineRunner | MUST HAVE | JPA/Hibernate Entity Model | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ----JPA/Hibernate Entity Model---- Create entities: User, Role, Vendor, Item, PR, PO. Establish relationships: One-to-Many, Many-to-One. Add JPA validation annotations. Configure ID generation strategies. Test repository queries using CommandLineRunner | MUST HAVE | JPA/Hibernate Entity Model | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ----JPA/Hibernate Entity Model---- Create entities: User, Role, Vendor, Item, PR, PO. Establish relationships: One-to-Many, Many-to-One. Add JPA validation annotations. Configure ID generation strategies. Test repository queries using CommandLineRunner | MUST HAVE | JPA/Hibernate Entity Model | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ----JPA/Hibernate Entity Model---- Create entities: User, Role, Vendor, Item, PR, PO. Establish relationships: One-to-Many, Many-to-One. Add JPA validation annotations. Configure ID generation strategies. Test repository queries using CommandLineRunner | MUST HAVE | JPA/Hibernate Entity Model | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ---Basic REST Controllers--- Implement sample CRUD controller (/api/test). Expose health check API (/health). Build a simple DTO + Mapper pattern. Test APIs using Postman. Return proper JSON responses using ResponseEntity. | MUST HAVE | Basic REST Controllers | Team 4 | 3- Completed
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ---Basic REST Controllers--- Implement sample CRUD controller (/api/test). Expose health check API (/health). Build a simple DTO + Mapper pattern. Test APIs using Postman. Return proper JSON responses using ResponseEntity. | MUST HAVE | Basic REST Controllers | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ---Basic REST Controllers--- Implement sample CRUD controller (/api/test). Expose health check API (/health). Build a simple DTO + Mapper pattern. Test APIs using Postman. Return proper JSON responses using ResponseEntity. | MUST HAVE | Basic REST Controllers | Team 4 | 3- Completed
|  | InternT4 - 019(Ajay Paladugula) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ---Basic REST Controllers--- Implement sample CRUD controller (/api/test). Expose health check API (/health). Build a simple DTO + Mapper pattern. Test APIs using Postman. Return proper JSON responses using ResponseEntity. | MUST HAVE | Basic REST Controllers | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs ---Basic REST Controllers--- Implement sample CRUD controller (/api/test). Expose health check API (/health). Build a simple DTO + Mapper pattern. Test APIs using Postman. Return proper JSON responses using ResponseEntity. | MUST HAVE | Basic REST Controllers | Team 4 | 3- Completed
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---Logging & Build Automation--- Configure application logging (SLF4J + Logback). Add log patterns for module identifiers. Set up Maven build pipeline. Package app as JAR and run from command. Create README.md with setup instructions. | MUST HAVE | Logging & Build Automation | Team 5 | 3- Completed
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---Logging & Build Automation--- Configure application logging (SLF4J + Logback). Add log patterns for module identifiers. Set up Maven build pipeline. Package app as JAR and run from command. Create README.md with setup instructions. | MUST HAVE | Logging & Build Automation | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---Logging & Build Automation--- Configure application logging (SLF4J + Logback). Add log patterns for module identifiers. Set up Maven build pipeline. Package app as JAR and run from command. Create README.md with setup instructions. | MUST HAVE | Logging & Build Automation | Team 5 | 2- In Progress
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---Logging & Build Automation--- Configure application logging (SLF4J + Logback). Add log patterns for module identifiers. Set up Maven build pipeline. Package app as JAR and run from command. Create README.md with setup instructions. | MUST HAVE | Logging & Build Automation | Team 5 | 3- Completed
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Introduce Java tools, Spring Boot basics, and best practices; gather requirements for framework design; Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; Build vendor data models, define procurement workflows, set up APIs. ---Logging & Build Automation--- Configure application logging (SLF4J + Logback). Add log patterns for module identifiers. Set up Maven build pipeline. Package app as JAR and run from command. Create README.md with setup instructions. | MUST HAVE | Logging & Build Automation | Team 5 | 1- Not Started
Sprint 2 | Sprint 2 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Implement login API (/auth/login). Create JWT token generator + validator. Create authentication filter. Store hashed passwords (BCrypt). Test token flow using Postman. | MUST HAVE | JWT Authentication | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Implement login API (/auth/login). Create JWT token generator + validator. Create authentication filter. Store hashed passwords (BCrypt). Test token flow using Postman. | MUST HAVE | JWT Authentication | Team 1 | 3- Completed
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Implement login API (/auth/login). Create JWT token generator + validator. Create authentication filter. Store hashed passwords (BCrypt). Test token flow using Postman. | MUST HAVE | JWT Authentication | Team 1 | 3- Completed
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Implement login API (/auth/login). Create JWT token generator + validator. Create authentication filter. Store hashed passwords (BCrypt). Test token flow using Postman. | MUST HAVE | JWT Authentication | Team 1 | 3- Completed
|  | InternT1 - 005(Haritha p - 3rd ECE) | Implement login API (/auth/login). Create JWT token generator + validator. Create authentication filter. Store hashed passwords (BCrypt). Test token flow using Postman. | MUST HAVE | JWT Authentication | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) | Implement /auth/register. Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). Create UserRole join table. Validate user registration (email, length). Seed default admin user. | MUST HAVE | User Registration + Role Mapping | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Implement /auth/register. Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). Create UserRole join table. Validate user registration (email, length). Seed default admin user. | MUST HAVE | User Registration + Role Mapping | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Implement /auth/register. Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). Create UserRole join table. Validate user registration (email, length). Seed default admin user. | MUST HAVE | User Registration + Role Mapping | Team 2 | 2- In Progress
|  | InternT2 - 009(Bade Navya - 4th CSE) | Implement /auth/register. Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). Create UserRole join table. Validate user registration (email, length). Seed default admin user. | MUST HAVE | User Registration + Role Mapping | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Implement /auth/register. Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). Create UserRole join table. Validate user registration (email, length). Seed default admin user. | MUST HAVE | User Registration + Role Mapping | Team 2 | 3- Completed
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Apply Spring Security on module endpoints. Implement access rules (Admin-only, Finance-only, Vendor-only). Test unauthorized access scenarios. Build SecurityConfig (filter chain). Implement logout (token blacklist optional). | MUST HAVE | Securing Endpoints (RBAC) | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Apply Spring Security on module endpoints. Implement access rules (Admin-only, Finance-only, Vendor-only). Test unauthorized access scenarios. Build SecurityConfig (filter chain). Implement logout (token blacklist optional). | MUST HAVE | Securing Endpoints (RBAC) | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Apply Spring Security on module endpoints. Implement access rules (Admin-only, Finance-only, Vendor-only). Test unauthorized access scenarios. Build SecurityConfig (filter chain). Implement logout (token blacklist optional). | MUST HAVE | Securing Endpoints (RBAC) | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Apply Spring Security on module endpoints. Implement access rules (Admin-only, Finance-only, Vendor-only). Test unauthorized access scenarios. Build SecurityConfig (filter chain). Implement logout (token blacklist optional). | MUST HAVE | Securing Endpoints (RBAC) | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Apply Spring Security on module endpoints. Implement access rules (Admin-only, Finance-only, Vendor-only). Test unauthorized access scenarios. Build SecurityConfig (filter chain). Implement logout (token blacklist optional). | MUST HAVE | Securing Endpoints (RBAC) | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Create audit table for login events. Write interceptor for logging user actions. Log timestamp, userId, action, requestPath. Implement audit REST API for admin. Export audit logs as CSV. | MUST HAVE | Audit Logging | Team 4 | 3- Completed
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Create audit table for login events. Write interceptor for logging user actions. Log timestamp, userId, action, requestPath. Implement audit REST API for admin. Export audit logs as CSV. | MUST HAVE | Audit Logging | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Create audit table for login events. Write interceptor for logging user actions. Log timestamp, userId, action, requestPath. Implement audit REST API for admin. Export audit logs as CSV. | MUST HAVE | Audit Logging | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Create audit table for login events. Write interceptor for logging user actions. Log timestamp, userId, action, requestPath. Implement audit REST API for admin. Export audit logs as CSV. | MUST HAVE | Audit Logging | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Create audit table for login events. Write interceptor for logging user actions. Log timestamp, userId, action, requestPath. Implement audit REST API for admin. Export audit logs as CSV. | MUST HAVE | Audit Logging | Team 4 | 3- Completed
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Integrate Swagger/OpenAPI. Add bearer token input in Swagger UI. Document all authentication endpoints. Add example request/response bodies. Publish API documentation PDF. | MUST HAVE | Logging & Build Automation | Team 5 | 3- Completed
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Integrate Swagger/OpenAPI. Add bearer token input in Swagger UI. Document all authentication endpoints. Add example request/response bodies. Publish API documentation PDF. | MUST HAVE | Logging & Build Automation | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Integrate Swagger/OpenAPI. Add bearer token input in Swagger UI. Document all authentication endpoints. Add example request/response bodies. Publish API documentation PDF. | MUST HAVE | Logging & Build Automation | Team 5 | 2- In Progress
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Integrate Swagger/OpenAPI. Add bearer token input in Swagger UI. Document all authentication endpoints. Add example request/response bodies. Publish API documentation PDF. | MUST HAVE | Logging & Build Automation | Team 5 | 3- Completed
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Integrate Swagger/OpenAPI. Add bearer token input in Swagger UI. Document all authentication endpoints. Add example request/response bodies. Publish API documentation PDF. | MUST HAVE | Logging & Build Automation | Team 5 | 1- Not Started
Sprint 3 | Sprint 3 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Create APIs: add, update, delete, getById. Validate vendor fields (GST, email, rating). Implement soft-delete instead of hard-delete. Create Vendor DTO + Mapper. Build Postman collection for vendor APIs. | MUST HAVE | Vendor CRUD API | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Create APIs: add, update, delete, getById. Validate vendor fields (GST, email, rating). Implement soft-delete instead of hard-delete. Create Vendor DTO + Mapper. Build Postman collection for vendor APIs. | MUST HAVE | Vendor CRUD API | Team 1 | 3- Completed
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Create APIs: add, update, delete, getById. Validate vendor fields (GST, email, rating). Implement soft-delete instead of hard-delete. Create Vendor DTO + Mapper. Build Postman collection for vendor APIs. | MUST HAVE | Vendor CRUD API | Team 1 | 3- Completed
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Create APIs: add, update, delete, getById. Validate vendor fields (GST, email, rating). Implement soft-delete instead of hard-delete. Create Vendor DTO + Mapper. Build Postman collection for vendor APIs. | MUST HAVE | Vendor CRUD API | Team 1 | 3- Completed
|  | InternT1 - 005(Haritha p - 3rd ECE) | Create APIs: add, update, delete, getById. Validate vendor fields (GST, email, rating). Implement soft-delete instead of hard-delete. Create Vendor DTO + Mapper. Build Postman collection for vendor APIs. | MUST HAVE | Vendor CRUD API | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) | Build API: /vendors/search. Add filters: rating, location, category, compliance. Implement pagination with Pageable. Add sorting support. Perform load testing on search API. | MUST HAVE | Vendor Search & Filters | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Build API: /vendors/search. Add filters: rating, location, category, compliance. Implement pagination with Pageable. Add sorting support. Perform load testing on search API. | MUST HAVE | Vendor Search & Filters | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Build API: /vendors/search. Add filters: rating, location, category, compliance. Implement pagination with Pageable. Add sorting support. Perform load testing on search API. | MUST HAVE | Vendor Search & Filters | Team 2 | 2- In Progress
|  | InternT2 - 009(Bade Navya - 4th CSE) | Build API: /vendors/search. Add filters: rating, location, category, compliance. Implement pagination with Pageable. Add sorting support. Perform load testing on search API. | MUST HAVE | Vendor Search & Filters | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Build API: /vendors/search. Add filters: rating, location, category, compliance. Implement pagination with Pageable. Add sorting support. Perform load testing on search API. | MUST HAVE | Vendor Search & Filters | Team 2 | 3- Completed
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Upload vendor documents (PDF/Image). Store docs in DB/File system. Add compliance verification flags. Add compliance status history table. Build API to download stored documents. | MUST HAVE | Vendor Compliance Module | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Upload vendor documents (PDF/Image). Store docs in DB/File system. Add compliance verification flags. Add compliance status history table. Build API to download stored documents. | MUST HAVE | Vendor Compliance Module | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Upload vendor documents (PDF/Image). Store docs in DB/File system. Add compliance verification flags. Add compliance status history table. Build API to download stored documents. | MUST HAVE | Vendor Compliance Module | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Upload vendor documents (PDF/Image). Store docs in DB/File system. Add compliance verification flags. Add compliance status history table. Build API to download stored documents. | MUST HAVE | Vendor Compliance Module | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Upload vendor documents (PDF/Image). Store docs in DB/File system. Add compliance verification flags. Add compliance status history table. Build API to download stored documents. | MUST HAVE | Vendor Compliance Module | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Create vendor score calculation logic. Add fields: delivery rate, quality rating, price score. Write scheduled job to update performance scores. Build API to fetch performance summary. Create simple analytics query using JPQL. | MUST HAVE | Vendor Performance Tracking | Team 4 | 3- Completed
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Create vendor score calculation logic. Add fields: delivery rate, quality rating, price score. Write scheduled job to update performance scores. Build API to fetch performance summary. Create simple analytics query using JPQL. | MUST HAVE | Vendor Performance Tracking | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Create vendor score calculation logic. Add fields: delivery rate, quality rating, price score. Write scheduled job to update performance scores. Build API to fetch performance summary. Create simple analytics query using JPQL. | MUST HAVE | Vendor Performance Tracking | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Create vendor score calculation logic. Add fields: delivery rate, quality rating, price score. Write scheduled job to update performance scores. Build API to fetch performance summary. Create simple analytics query using JPQL. | MUST HAVE | Vendor Performance Tracking | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Create vendor score calculation logic. Add fields: delivery rate, quality rating, price score. Write scheduled job to update performance scores. Build API to fetch performance summary. Create simple analytics query using JPQL. | MUST HAVE | Vendor Performance Tracking | Team 4 | 3- Completed
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Create vendor listing HTML using Thymeleaf/React. Display vendor details & filter UI. Add form for new vendor registration. Add validation messages. Integrate with backend APIs. | MUST HAVE | Vendor UI (Optional Web UI) | Team 5 | 2- In Progress
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Create vendor listing HTML using Thymeleaf/React. Display vendor details & filter UI. Add form for new vendor registration. Add validation messages. Integrate with backend APIs. | MUST HAVE | Vendor UI (Optional Web UI) | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Create vendor listing HTML using Thymeleaf/React. Display vendor details & filter UI. Add form for new vendor registration. Add validation messages. Integrate with backend APIs. | MUST HAVE | Vendor UI (Optional Web UI) | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Create vendor listing HTML using Thymeleaf/React. Display vendor details & filter UI. Add form for new vendor registration. Add validation messages. Integrate with backend APIs. | MUST HAVE | Vendor UI (Optional Web UI) | Team 5 | 3- Completed
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Create vendor listing HTML using Thymeleaf/React. Display vendor details & filter UI. Add form for new vendor registration. Add validation messages. Integrate with backend APIs. | MUST HAVE | Vendor UI (Optional Web UI) | Team 5 | 1- Not Started
Sprint 4 | Sprint 4 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Implement a PR model (items, quantity, budget). Create API: Create PR, update PR. Auto-generate PR number. Validation rules for budget limits. Test with JSON payloads. | MUST HAVE | Procurement Request (PR) Module | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Implement a PR model (items, quantity, budget). Create API: Create PR, update PR. Auto-generate PR number. Validation rules for budget limits. Test with JSON payloads. | MUST HAVE | Procurement Request (PR) Module | Team 1 | 3- Completed
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Implement a PR model (items, quantity, budget). Create API: Create PR, update PR. Auto-generate PR number. Validation rules for budget limits. Test with JSON payloads. | MUST HAVE | Procurement Request (PR) Module | Team 1 | 3- Completed
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Implement a PR model (items, quantity, budget). Create API: Create PR, update PR. Auto-generate PR number. Validation rules for budget limits. Test with JSON payloads. | MUST HAVE | Procurement Request (PR) Module | Team 1 | 1- Not Started
|  | InternT1 - 005(Haritha p - 3rd ECE) | Implement a PR model (items, quantity, budget). Create API: Create PR, update PR. Auto-generate PR number. Validation rules for budget limits. Test with JSON payloads. | MUST HAVE | Procurement Request (PR) Module | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) | Workflow states: Draft → Submitted → Approved → Rejected. API for approving/rejecting requests. Record approval history. Add comments section for approvers. Prevent unauthorized approvals. | MUST HAVE | Multi-Level Approval Workflow | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Workflow states: Draft → Submitted → Approved → Rejected. API for approving/rejecting requests. Record approval history. Add comments section for approvers. Prevent unauthorized approvals. | MUST HAVE | Multi-Level Approval Workflow | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Workflow states: Draft → Submitted → Approved → Rejected. API for approving/rejecting requests. Record approval history. Add comments section for approvers. Prevent unauthorized approvals. | MUST HAVE | Multi-Level Approval Workflow | Team 2 | 2- In Progress
|  | InternT2 - 009(Bade Navya - 4th CSE) | Workflow states: Draft → Submitted → Approved → Rejected. API for approving/rejecting requests. Record approval history. Add comments section for approvers. Prevent unauthorized approvals. | MUST HAVE | Multi-Level Approval Workflow | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Workflow states: Draft → Submitted → Approved → Rejected. API for approving/rejecting requests. Record approval history. Add comments section for approvers. Prevent unauthorized approvals. | MUST HAVE | Multi-Level Approval Workflow | Team 2 | 2- In Progress
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Add & update PR line items. Validate item price and quantity. Link PR with vendor quotes. Implement delete/reorder item logic. Calculate PR estimated cost. | MUST HAVE | PR Item Management | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Add & update PR line items. Validate item price and quantity. Link PR with vendor quotes. Implement delete/reorder item logic. Calculate PR estimated cost. | MUST HAVE | PR Item Management | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Add & update PR line items. Validate item price and quantity. Link PR with vendor quotes. Implement delete/reorder item logic. Calculate PR estimated cost. | MUST HAVE | PR Item Management | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Add & update PR line items. Validate item price and quantity. Link PR with vendor quotes. Implement delete/reorder item logic. Calculate PR estimated cost. | MUST HAVE | PR Item Management | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Add & update PR line items. Validate item price and quantity. Link PR with vendor quotes. Implement delete/reorder item logic. Calculate PR estimated cost. | MUST HAVE | PR Item Management | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Send email on PR submission & approval. Build notification templates. Use JavaMailSender. Store email logs. Retry logic for failed emails. | MUST HAVE | PR Notifications | Team 4 | 3- Completed
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Send email on PR submission & approval. Build notification templates. Use JavaMailSender. Store email logs. Retry logic for failed emails. | MUST HAVE | PR Notifications | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Send email on PR submission & approval. Build notification templates. Use JavaMailSender. Store email logs. Retry logic for failed emails. | MUST HAVE | PR Notifications | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Send email on PR submission & approval. Build notification templates. Use JavaMailSender. Store email logs. Retry logic for failed emails. | MUST HAVE | PR Notifications | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Send email on PR submission & approval. Build notification templates. Use JavaMailSender. Store email logs. Retry logic for failed emails. | MUST HAVE | PR Notifications | Team 4 | 3- Completed
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Fetch pending PRs. Fetch completed PRs. Filter PRs by department/user. Search PRs by date. Create summary API for home dashboard. | MUST HAVE | PR Dashboard API | Team 5 | 1- Not Started
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Fetch pending PRs. Fetch completed PRs. Filter PRs by department/user. Search PRs by date. Create summary API for home dashboard. | MUST HAVE | PR Dashboard API | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Fetch pending PRs. Fetch completed PRs. Filter PRs by department/user. Search PRs by date. Create summary API for home dashboard. | MUST HAVE | PR Dashboard API | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Fetch pending PRs. Fetch completed PRs. Filter PRs by department/user. Search PRs by date. Create summary API for home dashboard. | MUST HAVE | PR Dashboard API | Team 5 | 3- Completed
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Fetch pending PRs. Fetch completed PRs. Filter PRs by department/user. Search PRs by date. Create summary API for home dashboard. | MUST HAVE | PR Dashboard API | Team 5 | 1- Not Started
Sprint 5 | Sprint 5 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Create PO from PR. Auto-generate PO number. Validate vendor availability. Validate approved PR only. Add PO comments & terms. | MUST HAVE | PO Generation APIs | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Create PO from PR. Auto-generate PO number. Validate vendor availability. Validate approved PR only. Add PO comments & terms. | MUST HAVE | PO Generation APIs | Team 1 | 3- Completed
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Create PO from PR. Auto-generate PO number. Validate vendor availability. Validate approved PR only. Add PO comments & terms. | MUST HAVE | PO Generation APIs | Team 1 | 3- Completed
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Create PO from PR. Auto-generate PO number. Validate vendor availability. Validate approved PR only. Add PO comments & terms. | MUST HAVE | PO Generation APIs | Team 1 | 1- Not Started
|  | InternT1 - 005(Haritha p - 3rd ECE) | Create PO from PR. Auto-generate PO number. Validate vendor availability. Validate approved PR only. Add PO comments & terms. | MUST HAVE | PO Generation APIs | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) g1 | Add line items with quantity, tax, discount. Calculate subtotal + tax + total cost. Update item quantity and price. Close PO once delivered. Add item delivery status. | MUST HAVE | PO Item Management | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Add line items with quantity, tax, discount. Calculate subtotal + tax + total cost. Update item quantity and price. Close PO once delivered. Add item delivery status. | MUST HAVE | PO Item Management | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Add line items with quantity, tax, discount. Calculate subtotal + tax + total cost. Update item quantity and price. Close PO once delivered. Add item delivery status. | MUST HAVE | PO Item Management | Team 2 | 1- Not Started
|  | InternT2 - 009(Bade Navya - 4th CSE) | Add line items with quantity, tax, discount. Calculate subtotal + tax + total cost. Update item quantity and price. Close PO once delivered. Add item delivery status. | MUST HAVE | PO Item Management | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Add line items with quantity, tax, discount. Calculate subtotal + tax + total cost. Update item quantity and price. Close PO once delivered. Add item delivery status. | MUST HAVE | PO Item Management | Team 2 | 1- Not Started
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Record delivery dates & timelines. Add partial delivery support. Add remarks for damaged/returned items. Update PO status accordingly. Add delivery confirmation API. | MUST HAVE | PO Delivery Tracking | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Record delivery dates & timelines. Add partial delivery support. Add remarks for damaged/returned items. Update PO status accordingly. Add delivery confirmation API. | MUST HAVE | PO Delivery Tracking | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Record delivery dates & timelines. Add partial delivery support. Add remarks for damaged/returned items. Update PO status accordingly. Add delivery confirmation API. | MUST HAVE | PO Delivery Tracking | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Record delivery dates & timelines. Add partial delivery support. Add remarks for damaged/returned items. Update PO status accordingly. Add delivery confirmation API. | MUST HAVE | PO Delivery Tracking | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Record delivery dates & timelines. Add partial delivery support. Add remarks for damaged/returned items. Update PO status accordingly. Add delivery confirmation API. | MUST HAVE | PO Delivery Tracking | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Validate total cost against budgets. Log financial approvals. Secure financial data with role restrictions. Add expenditure summary table. Add cost-center mapping. | MUST HAVE | Financial Validation | Team 4 | 2- In Progress
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Validate total cost against budgets. Log financial approvals. Secure financial data with role restrictions. Add expenditure summary table. Add cost-center mapping. | MUST HAVE | Financial Validation | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Validate total cost against budgets. Log financial approvals. Secure financial data with role restrictions. Add expenditure summary table. Add cost-center mapping. | MUST HAVE | Financial Validation | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Validate total cost against budgets. Log financial approvals. Secure financial data with role restrictions. Add expenditure summary table. Add cost-center mapping. | MUST HAVE | Financial Validation | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Validate total cost against budgets. Log financial approvals. Secure financial data with role restrictions. Add expenditure summary table. Add cost-center mapping. | MUST HAVE | Financial Validation | Team 4 | 1- Not Started
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Search PO by vendor, cost, date range. Sort by delivery timeline. Paginated PO listing. Export PO list as CSV. Build Postman collection for PO module. | MUST HAVE | PO Search & Filters | Team 5 | 1- Not Started
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Search PO by vendor, cost, date range. Sort by delivery timeline. Paginated PO listing. Export PO list as CSV. Build Postman collection for PO module. | MUST HAVE | PO Search & Filters | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Search PO by vendor, cost, date range. Sort by delivery timeline. Paginated PO listing. Export PO list as CSV. Build Postman collection for PO module. | MUST HAVE | PO Search & Filters | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Search PO by vendor, cost, date range. Sort by delivery timeline. Paginated PO listing. Export PO list as CSV. Build Postman collection for PO module. | MUST HAVE | PO Search & Filters | Team 5 | 2- In Progress
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Search PO by vendor, cost, date range. Sort by delivery timeline. Paginated PO listing. Export PO list as CSV. Build Postman collection for PO module. | MUST HAVE | PO Search & Filters | Team 5 | 1- Not Started
Sprint 6 | Sprint 6 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Create JRXML templates (Vendor, PR, PO). Add headers, footers, table components. Use parameters & fields. Apply formatting & page breaks. Test with sample data. | MUST HAVE | Jasper Template Design | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Create JRXML templates (Vendor, PR, PO). Add headers, footers, table components. Use parameters & fields. Apply formatting & page breaks. Test with sample data. | MUST HAVE | Jasper Template Design | Team 1 | 2- In Progress
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Create JRXML templates (Vendor, PR, PO). Add headers, footers, table components. Use parameters & fields. Apply formatting & page breaks. Test with sample data. | MUST HAVE | Jasper Template Design | Team 1 | 1- Not Started
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Create JRXML templates (Vendor, PR, PO). Add headers, footers, table components. Use parameters & fields. Apply formatting & page breaks. Test with sample data. | MUST HAVE | Jasper Template Design | Team 1 | 1- Not Started
|  | InternT1 - 005(Haritha p - 3rd ECE) | Create JRXML templates (Vendor, PR, PO). Add headers, footers, table components. Use parameters & fields. Apply formatting & page breaks. Test with sample data. | MUST HAVE | Jasper Template Design | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) g1 | Build API: /reports/vendor Build API: /reports/pr Build API: /reports/po Integrate JasperReports Java library. Return PDF/Excel output streams. | MUST HAVE | Report Generation API | Team 2 | 3- Completed
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Build API: /reports/vendor Build API: /reports/pr Build API: /reports/po Integrate JasperReports Java library. Return PDF/Excel output streams. | MUST HAVE | Report Generation API | Team 2 | 3- Completed
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Build API: /reports/vendor Build API: /reports/pr Build API: /reports/po Integrate JasperReports Java library. Return PDF/Excel output streams. | MUST HAVE | Report Generation API | Team 2 | 1- Not Started
|  | InternT2 - 009(Bade Navya - 4th CSE) | Build API: /reports/vendor Build API: /reports/pr Build API: /reports/po Integrate JasperReports Java library. Return PDF/Excel output streams. | MUST HAVE | Report Generation API | Team 2 | 3- Completed
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Build API: /reports/vendor Build API: /reports/pr Build API: /reports/po Integrate JasperReports Java library. Return PDF/Excel output streams. | MUST HAVE | Report Generation API | Team 2 | 1- Not Started
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Write SQL for monthly spending. Vendor performance analytics SQL. PR approval timeline SQL. Order fulfillment rate SQL. Use stored procedures for heavy reports. | MUST HAVE | Analytics SQL Queries | Team 3 | 3- Completed
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Write SQL for monthly spending. Vendor performance analytics SQL. PR approval timeline SQL. Order fulfillment rate SQL. Use stored procedures for heavy reports. | MUST HAVE | Analytics SQL Queries | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Write SQL for monthly spending. Vendor performance analytics SQL. PR approval timeline SQL. Order fulfillment rate SQL. Use stored procedures for heavy reports. | MUST HAVE | Analytics SQL Queries | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Write SQL for monthly spending. Vendor performance analytics SQL. PR approval timeline SQL. Order fulfillment rate SQL. Use stored procedures for heavy reports. | MUST HAVE | Analytics SQL Queries | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Write SQL for monthly spending. Vendor performance analytics SQL. PR approval timeline SQL. Order fulfillment rate SQL. Use stored procedures for heavy reports. | MUST HAVE | Analytics SQL Queries | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Build dashboard summary API. Create KPI endpoints (cost savings, lead time). Fetch multi-module aggregated data. Cache expensive queries. Optimize using projections. | MUST HAVE | Dashboard Backend API | Team 4 | 1- Not Started
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Build dashboard summary API. Create KPI endpoints (cost savings, lead time). Fetch multi-module aggregated data. Cache expensive queries. Optimize using projections. | MUST HAVE | Dashboard Backend API | Team 4 | 3- Completed
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Build dashboard summary API. Create KPI endpoints (cost savings, lead time). Fetch multi-module aggregated data. Cache expensive queries. Optimize using projections. | MUST HAVE | Dashboard Backend API | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Build dashboard summary API. Create KPI endpoints (cost savings, lead time). Fetch multi-module aggregated data. Cache expensive queries. Optimize using projections. | MUST HAVE | Dashboard Backend API | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Build dashboard summary API. Create KPI endpoints (cost savings, lead time). Fetch multi-module aggregated data. Cache expensive queries. Optimize using projections. | MUST HAVE | Dashboard Backend API | Team 4 | 1- Not Started
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Create scheduler using @Scheduled. Email daily/weekly reports. Store generated reports in DB. Retry mechanism for failed jobs. Build report history API. | MUST HAVE | Report Scheduler | Team 5 | 1- Not Started
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Create scheduler using @Scheduled. Email daily/weekly reports. Store generated reports in DB. Retry mechanism for failed jobs. Build report history API. | MUST HAVE | Report Scheduler | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Create scheduler using @Scheduled. Email daily/weekly reports. Store generated reports in DB. Retry mechanism for failed jobs. Build report history API. | MUST HAVE | Report Scheduler | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Create scheduler using @Scheduled. Email daily/weekly reports. Store generated reports in DB. Retry mechanism for failed jobs. Build report history API. | MUST HAVE | Report Scheduler | Team 5 | 1- Not Started
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Create scheduler using @Scheduled. Email daily/weekly reports. Store generated reports in DB. Retry mechanism for failed jobs. Build report history API. | MUST HAVE | Report Scheduler | Team 5 | 1- Not Started
Sprint 7 | Sprint 7 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Use JMeter/Postman Runner. Load test PR approval workflow. Load test vendor search. Compare performance pre/post optimizations. Generate performance reports. | MUST HAVE | API Load Testing | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Use JMeter/Postman Runner. Load test PR approval workflow. Load test vendor search. Compare performance pre/post optimizations. Generate performance reports. | MUST HAVE | API Load Testing | Team 1 | 1- Not Started
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Use JMeter/Postman Runner. Load test PR approval workflow. Load test vendor search. Compare performance pre/post optimizations. Generate performance reports. | MUST HAVE | API Load Testing | Team 1 | 1- Not Started
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Use JMeter/Postman Runner. Load test PR approval workflow. Load test vendor search. Compare performance pre/post optimizations. Generate performance reports. | MUST HAVE | API Load Testing | Team 1 | 1- Not Started
|  | InternT1 - 005(Haritha p - 3rd ECE) | Use JMeter/Postman Runner. Load test PR approval workflow. Load test vendor search. Compare performance pre/post optimizations. Generate performance reports. | MUST HAVE | API Load Testing | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) g1 | JUnit test for controllers. MockMvc for API tests. Test repositories with Testcontainers. Service layer mocking with Mockito. Generate coverage reports. | MUST HAVE | Unit & Integration Testing | Team 2 | 2- In Progress
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | JUnit test for controllers. MockMvc for API tests. Test repositories with Testcontainers. Service layer mocking with Mockito. Generate coverage reports. | MUST HAVE | Unit & Integration Testing | Team 2 | 1- Not Started
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | JUnit test for controllers. MockMvc for API tests. Test repositories with Testcontainers. Service layer mocking with Mockito. Generate coverage reports. | MUST HAVE | Unit & Integration Testing | Team 2 | 1- Not Started
|  | InternT2 - 009(Bade Navya - 4th CSE) | JUnit test for controllers. MockMvc for API tests. Test repositories with Testcontainers. Service layer mocking with Mockito. Generate coverage reports. | MUST HAVE | Unit & Integration Testing | Team 2 | 1- Not Started
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | JUnit test for controllers. MockMvc for API tests. Test repositories with Testcontainers. Service layer mocking with Mockito. Generate coverage reports. | MUST HAVE | Unit & Integration Testing | Team 2 | 1- Not Started
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Add missing indexes. Analyze slow queries. Benchmark read/write performance. Optimize Hibernate queries. Tune connection pool (HikariCP). | MUST HAVE | Database Optimization | Team 3 | 1- Not Started
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Add missing indexes. Analyze slow queries. Benchmark read/write performance. Optimize Hibernate queries. Tune connection pool (HikariCP). | MUST HAVE | Database Optimization | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Add missing indexes. Analyze slow queries. Benchmark read/write performance. Optimize Hibernate queries. Tune connection pool (HikariCP). | MUST HAVE | Database Optimization | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Add missing indexes. Analyze slow queries. Benchmark read/write performance. Optimize Hibernate queries. Tune connection pool (HikariCP). | MUST HAVE | Database Optimization | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Add missing indexes. Analyze slow queries. Benchmark read/write performance. Optimize Hibernate queries. Tune connection pool (HikariCP). | MUST HAVE | Database Optimization | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | Test for SQL Injection. Test for broken RBAC rules. Validate JWT expiration logic. Implement rate limiting on sensitive endpoints. Secure environment variables & config. | MUST HAVE | Security Testing | Team 4 | 1- Not Started
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | Test for SQL Injection. Test for broken RBAC rules. Validate JWT expiration logic. Implement rate limiting on sensitive endpoints. Secure environment variables & config. | MUST HAVE | Security Testing | Team 4 | 1- Not Started
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | Test for SQL Injection. Test for broken RBAC rules. Validate JWT expiration logic. Implement rate limiting on sensitive endpoints. Secure environment variables & config. | MUST HAVE | Security Testing | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | Test for SQL Injection. Test for broken RBAC rules. Validate JWT expiration logic. Implement rate limiting on sensitive endpoints. Secure environment variables & config. | MUST HAVE | Security Testing | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | Test for SQL Injection. Test for broken RBAC rules. Validate JWT expiration logic. Implement rate limiting on sensitive endpoints. Secure environment variables & config. | MUST HAVE | Security Testing | Team 4 | 1- Not Started
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Create GitHub Actions/Maven pipeline. Compile, test, package automatically. Push JAR to Artifactory/S3. Trigger deployments on commit. Add sonar code quality checks. | MUST HAVE | CI/CD Setup | Team 5 | 1- Not Started
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Create GitHub Actions/Maven pipeline. Compile, test, package automatically. Push JAR to Artifactory/S3. Trigger deployments on commit. Add sonar code quality checks. | MUST HAVE | CI/CD Setup | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Create GitHub Actions/Maven pipeline. Compile, test, package automatically. Push JAR to Artifactory/S3. Trigger deployments on commit. Add sonar code quality checks. | MUST HAVE | CI/CD Setup | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Create GitHub Actions/Maven pipeline. Compile, test, package automatically. Push JAR to Artifactory/S3. Trigger deployments on commit. Add sonar code quality checks. | MUST HAVE | CI/CD Setup | Team 5 | 1- Not Started
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Create GitHub Actions/Maven pipeline. Compile, test, package automatically. Push JAR to Artifactory/S3. Trigger deployments on commit. Add sonar code quality checks. | MUST HAVE | CI/CD Setup | Team 5 | 1- Not Started
Sprint 8 | Sprint 8 | InternT1 - 001(Deepak Chandhru N - 4th year (IT)) | Create Dockerfile for the project. Add multi-stage build. Create docker-compose. Configure DB container. Deploy locally in one command. | MUST HAVE | Docker Deployment | Team 1 | 1- Not Started
|  | InternT1 - 002(Gajulapalli Naga Lahari - 3rd year (CSE)) | Create Dockerfile for the project. Add multi-stage build. Create docker-compose. Configure DB container. Deploy locally in one command. | MUST HAVE | Docker Deployment | Team 1 | 1- Not Started
|  | InternT1 - 003(Karthik Prasanna - 3rd year (IT)) | Create Dockerfile for the project. Add multi-stage build. Create docker-compose. Configure DB container. Deploy locally in one command. | MUST HAVE | Docker Deployment | Team 1 | 1- Not Started
|  | InternT1 - 004(Dommata Dhanush - 4th year(CSE) ) | Create Dockerfile for the project. Add multi-stage build. Create docker-compose. Configure DB container. Deploy locally in one command. | MUST HAVE | Docker Deployment | Team 1 | 1- Not Started
|  | InternT1 - 005(Haritha p - 3rd ECE) | Create Dockerfile for the project. Add multi-stage build. Create docker-compose. Configure DB container. Deploy locally in one command. | MUST HAVE | Docker Deployment | Team 1 | 1- Not Started
|  | InternT2 - 006(Vemula Padma Priya-Graduate 2025(CSE)) g1 | Test all modules end-to-end. Fix final bugs & data issues. Re-run all workflow scenarios. Validate reporting module. Validate role-based access for users. | MUST HAVE | Final QA Testing | Team 2 | 2- In Progress
|  | InternT2 - 007(K Ganesh kumar rao -- 3rd year (CSE)) | Test all modules end-to-end. Fix final bugs & data issues. Re-run all workflow scenarios. Validate reporting module. Validate role-based access for users. | MUST HAVE | Final QA Testing | Team 2 | 1- Not Started
|  | InternT2 - 008(JITHENDRANADH MADAPARTHI- 3rd year (CSE)) | Test all modules end-to-end. Fix final bugs & data issues. Re-run all workflow scenarios. Validate reporting module. Validate role-based access for users. | MUST HAVE | Final QA Testing | Team 2 | 1- Not Started
|  | InternT2 - 009(Bade Navya - 4th CSE) | Test all modules end-to-end. Fix final bugs & data issues. Re-run all workflow scenarios. Validate reporting module. Validate role-based access for users. | MUST HAVE | Final QA Testing | Team 2 | 1- Not Started
|  | InternT2 - 010(Bijji Vaishnavi -MCA 2nd Year) | Test all modules end-to-end. Fix final bugs & data issues. Re-run all workflow scenarios. Validate reporting module. Validate role-based access for users. | MUST HAVE | Final QA Testing | Team 2 | 1- Not Started
|  | InternT3 - 011(Yash Saini-2nd Year (MCA)) | Externalize configs using environment variables. Secure DB credentials. JVM performance tuning. Enable actuator health checks. Configure log rotation. | MUST HAVE | Production Configuration | Team 3 | 1- Not Started
|  | InternT3 - 012(juhee saxena - 3rd year Btech(CSE)) | Externalize configs using environment variables. Secure DB credentials. JVM performance tuning. Enable actuator health checks. Configure log rotation. | MUST HAVE | Production Configuration | Team 3 | 3- Completed
|  | InternT3- 013(Vishal Kumar) | Externalize configs using environment variables. Secure DB credentials. JVM performance tuning. Enable actuator health checks. Configure log rotation. | MUST HAVE | Production Configuration | Team 3 | 1- Not Started
|  | InternT3- 014(KOTA VENKATA DARSHINI - 3rd year Btech(CSE)) | Externalize configs using environment variables. Secure DB credentials. JVM performance tuning. Enable actuator health checks. Configure log rotation. | MUST HAVE | Production Configuration | Team 3 | 1- Not Started
|  | Intern T3 - 015(Varun Annabeemoju - 3rd CSE) | Externalize configs using environment variables. Secure DB credentials. JVM performance tuning. Enable actuator health checks. Configure log rotation. | MUST HAVE | Production Configuration | Team 3 | 1- Not Started
|  | InternT4 - 016(Sakshi Bhingare - 4th year (CSE)) | System Architecture Document. API Documentation (Swagger export). DB Schema Document. Installation Guide. User Manual (Admin, Procurement, Finance). | MUST HAVE | Documentation | Team 4 | 1- Not Started
|  | InternT4 - 017(Umang Joshi - 4th year Btech(CSE)) | System Architecture Document. API Documentation (Swagger export). DB Schema Document. Installation Guide. User Manual (Admin, Procurement, Finance). | MUST HAVE | Documentation | Team 4 | 1- Not Started
|  | InternT4 - 018(Bayagadda Sai Sharanya - 4th year (CSE) ) | System Architecture Document. API Documentation (Swagger export). DB Schema Document. Installation Guide. User Manual (Admin, Procurement, Finance). | MUST HAVE | Documentation | Team 4 | 1- Not Started
|  | InternT4 - 019(Ajay Paladugula) | System Architecture Document. API Documentation (Swagger export). DB Schema Document. Installation Guide. User Manual (Admin, Procurement, Finance). | MUST HAVE | Documentation | Team 4 | 1- Not Started
|  | InternT4 - 020(Reshi Arasu D 3rd CSE) | System Architecture Document. API Documentation (Swagger export). DB Schema Document. Installation Guide. User Manual (Admin, Procurement, Finance). | MUST HAVE | Documentation | Team 4 | 1- Not Started
|  | Intern T5- 021(Subham soni - 4th year (CSE)) | Build demo script (Vendor → PR → PO → Reports). Create PPT for each module. Show analytics & dashboards. Demonstrate security + RBAC. Present system outcomes & benefits. | MUST HAVE | Final Presentation & Demo | Team 5 | 1- Not Started
|  | InternT5 - 022(Aswini Chintala- 4th year (CSE)) | Build demo script (Vendor → PR → PO → Reports). Create PPT for each module. Show analytics & dashboards. Demonstrate security + RBAC. Present system outcomes & benefits. | MUST HAVE | Final Presentation & Demo | Team 5 | 1- Not Started
|  | InternT5 - 023(Arun Y- 3rd year (CSE)) | Build demo script (Vendor → PR → PO → Reports). Create PPT for each module. Show analytics & dashboards. Demonstrate security + RBAC. Present system outcomes & benefits. | MUST HAVE | Final Presentation & Demo | Team 5 | 1- Not Started
|  | InternT5 - 024(Anuj Kumar Singh 4th year CSE) | Build demo script (Vendor → PR → PO → Reports). Create PPT for each module. Show analytics & dashboards. Demonstrate security + RBAC. Present system outcomes & benefits. | MUST HAVE | Final Presentation & Demo | Team 5 | 1- Not Started
|  | InternT5 - 025(Vani Akhila Jannavarapu) | Build demo script (Vendor → PR → PO → Reports). Create PPT for each module. Show analytics & dashboards. Demonstrate security + RBAC. Present system outcomes & benefits. | MUST HAVE | Final Presentation & Demo | Team 5 | 1- Not Started

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 349.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
IT1 001 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Deepak Chandhru N | Others | 3- Completed | 0.3
| T0002 | Gather requirements for framework design |  |  | Deepak Chandhru N |  | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Deepak Chandhru N |  | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Deepak Chandhru N |  | 3- Completed | 1
| T0005 | Project Setup (Spring Boot + Maven) |  |  | Deepak Chandhru N |  | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. |  |  | Deepak Chandhru N |  | 3- Completed | 3
| T0007 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO) |  |  | Deepak Chandhru N |  | 3- Completed | 3
| T0008 | Configure Maven dependencies (Web, JPA, Validation, Security). |  |  | Deepak Chandhru N |  | 3- Completed | 3
| T0009 | Set up folder structure following clean architecture. |  |  | Deepak Chandhru N |  | 3- Completed | 3
| T0010 | Create environment profiles: dev, test, prod., implement global exception handler |  |  | Deepak Chandhru N |  | 2- In Progress | 3
IT1 002 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-29 | Gajulapalli Naga Lahari | Others | 3- Completed | 0.3
| T0002 | Gather requirements for framework design |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 1
| T0005 | Project Setup (Spring Boot + Maven) |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
| T0007 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO) |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
| T0008 | Configure Maven dependencies (Web, JPA, Validation, Security). |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
| T0009 | Set up folder structure following clean architecture. |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
| T0010 | Create environment profiles: dev, test, prod., implement global exception handler |  |  | Gajulapalli Naga Lahari |  | 3- Completed | 3
IT1 003 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Karthik Prasanna | Build | 2- In Progress
| T0002 | gather requirements for framework design; |  |  | Karthik Prasanna | Build | 2- In Progress
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Karthik Prasanna | Build | 3- Completed
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Karthik Prasanna | Build | 2- In Progress
| T0005 | Project Setup (Spring Boot + Maven) |  |  | Karthik Prasanna | Design | 3- Completed
| T0006 | Install/Configure MySQL or PostgreSQL. |  |  | Karthik Prasanna | Build | 3- Completed
| T0007 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO) |  |  | Karthik Prasanna | Coding | 2- In Progress
| T0008 | Configure Maven dependencies (Web, JPA, Validation, Security). |  |  | Karthik Prasanna | Coding | 1- Not Started
| T0009 | Set up folder structure following clean architecture. |  |  | Karthik Prasanna | Build | 1- Not Started
| T0010 | Create environment profiles: dev, test, prod., implement global exception handler |  |  | Karthik Prasanna | Coding | 1- Not Started
IT1 004 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-12-02 | 2025-12-02 | Dommata Dhanush | Others | 2- In Progress
| T0002 | Gather requirements for framework design |  |  | Dommata Dhanush
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Dommata Dhanush
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Dommata Dhanush
| T0005 | Project Setup (Spring Boot + Maven) |  |  | Dommata Dhanush
| T0006 | Install/Configure MySQL or PostgreSQL. |  |  | Dommata Dhanush
| T0007 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO) |  |  | Dommata Dhanush
| T0008 | Configure Maven dependencies (Web, JPA, Validation, Security). |  |  | Dommata Dhanush
| T0009 | Set up folder structure following clean architecture. |  |  | Dommata Dhanush
| T0010 | Create environment profiles: dev, test, prod., implement global exception handler |  |  | Dommata Dhanush
IT1 005 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-12-02 | 2025-12-02 | Haritha P | Others | 1- Not Started
| T0002 | Gather requirements for framework design |  |  | Haritha P
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Haritha P
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Haritha P
| T0005 | Project Setup (Spring Boot + Maven) |  |  | Haritha P
| T0006 | Install/Configure MySQL or PostgreSQL. |  |  | Haritha P
| T0007 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO) |  |  | Haritha P
| T0008 | Configure Maven dependencies (Web, JPA, Validation, Security). |  |  | Haritha P
| T0009 | Set up folder structure following clean architecture. |  |  | Haritha P
| T0010 | Create environment profiles: dev, test, prod., implement global exception handler |  |  | Haritha P
IT2 006 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-29 | Vemula Padma Priya | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 2025-12-01 | 2025-12-01 | Vemula Padma Priya | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-02 | 2025-12-02 | Vemula Padma Priya | Build | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-12-04 | 2025-12-06 | Vemula Padma Priya | Build | 3- Completed | 1
| T0005 | ---MySQL/PostgreSQL Configuration---- | 2025-12-03 | 2025-12-03 | Vemula Padma Priya | Build | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. | 2025-12-03 | 2025-12-03 | Vemula Padma Priya | Build | 3- Completed | 3
| T0007 | Create schema: spvms_db. | 2025-12-04 | 2025-12-04 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0007 | Write initial SQL tables (User, Roles, Vendor, PR, PO). | 2025-12-04 | 2025-12-04 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0009 | Integrate Flyway/Liquibase for DB migrations. | 2025-12-04 | 2025-12-04 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0010 | Test DB connection using Spring Boot | 2025-12-04 | 2025-12-04 | Vemula Padma Priya | Integration Test | 3- Completed | 3
| T0011 | Implement /auth/register. | 2025-12-08 | 2025-12-08 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0012 | Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). | 2025-12-09 | 2025-12-09 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0013 | Create UserRole join table. | 2025-12-10 | 2025-12-10 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0014 | Validate user registration (email, length). | 2025-12-11 | 2025-12-11 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0015 | Seed default admin user. | 2025-12-12 | 2025-12-12 | Vemula Padma Priya | Integration Test | 3- Completed | 3
| T0016 | Build API: /vendors/search. | 2025-12-15 | 2025-12-15 | Vemula Padma Priya | Build | 3- Completed | 3
| T0017 | Add filters: rating, location, category, compliance. | 2025-12-16 | 2025-12-16 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0018 | Implement pagination with Pageable. | 2025-12-17 | 2025-12-17 | Vemula Padma Priya | Coding | 3- Completed | 3
| T0019 | Add sorting support. | 2025-12-18 | 2025-12-18 | Vemula Padma Priya | Build | 3- Completed | 3
| T0020 | Perform load testing on search API. | 2025-12-19 | 2025-12-19 | Vemula Padma Priya | Build | 3- Completed | 3
| T0021 | Workflow states: Draft → Submitted → Approved → Rejected. |  |  | Vemula Padma Priya
| T0022 | API for approving/rejecting requests. |  |  | Vemula Padma Priya
| T0023 | Record approval history. |  |  | Vemula Padma Priya
| T0024 | Add comments section for approvers. |  |  | Vemula Padma Priya
| T0025 | Prevent unauthorized approvals. |  |  | Vemula Padma Priya
IT2 007 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-29 | K Ganesh Kumar Rao | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 2025-12-01 | 2025-12-01 | K Ganesh Kumar Rao | Others | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-02 | 2025-12-02 | K Ganesh Kumar Rao | Others | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-12-03 | 2025-12-04 | K Ganesh Kumar Rao | Coding | 3- Completed | 1
| T0005 | ---MySQL/PostgreSQL Configuration---- | 2025-12-03 | 2025-12-03 | K Ganesh Kumar Rao | Design | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. | 2025-12-03 | 2025-12-03 | K Ganesh Kumar Rao | Others | 3- Completed | 3
| T0007 | Create schema: spvms_db. | 2025-12-04 | 2025-12-04 | K Ganesh Kumar Rao | Coding | 3- Completed | 3
| T0008 | Write initial SQL tables (User, Roles, Vendor, PR, PO). | 2025-12-04 | 2025-12-04 | K Ganesh Kumar Rao | Coding | 3- Completed | 3
| T0009 | Integrate Flyway/Liquibase for DB migrations. | 2025-12-04 | 2025-12-04 | K Ganesh Kumar Rao | Integration Test | 3- Completed | 3
| T0010 | Test DB connection using Spring Boot. | 2025-12-04 | 2025-12-04 | K Ganesh Kumar Rao | Unit Test | 3- Completed | 3
IT2 008 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-29 | M.Jithendranadh | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 2025-12-01 | 2025-12-01 | M.Jithendranadh | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-02 | 2025-12-02 | M.Jithendranadh | Build | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-12-04 |  | M.Jithendranadh | Build | 1- Not Started | 1
| T0005 | ---MySQL/PostgreSQL Configuration---- | 2025-12-03 | 2025-12-03 | M.Jithendranadh | Build | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. | 2025-12-03 | 2025-12-03 | M.Jithendranadh | Build | 3- Completed | 3
| T0007 | Create schema: spvms_db. | 2025-12-04 | 2025-12-04 | M.Jithendranadh | Coding | 3- Completed | 3
| T0008 | Write initial SQL tables (User, Roles, Vendor, PR, PO). | 2025-12-04 | 2025-12-04 | M.Jithendranadh | Coding | 3- Completed | 3
| T0009 | Integrate Flyway/Liquibase for DB migrations. | 2025-12-04 | 2025-12-04 | M.Jithendranadh | Coding | 3- Completed | 3
| T0010 | Test DB connection using Spring Boot. | 2025-12-04 | 2025-12-04 | M.Jithendranadh | Integration Test | 3- Completed | 3
IT2 009 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-12-03 | 2025-12-04 | B.Navya | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 4/Dec/25 | 2025-12-05 | B.Navya | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-01 | 2025-12-05 | B.Navya | Build | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-12-06 | 2025-12-06 | B.Navya | Build | 3- Completed | 1
| T0005 | ---MySQL/PostgreSQL Configuration---- | 2025-12-05 | 2025-12-05 | B.Navya | Build | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. | 2025-12-05 | 2025-12-05 | B.Navya | Build | 3- Completed | 3
| T0007 | Create schema: spvms_db. | 2025-12-05 | 2025-12-05 | B.Navya | Coding | 3- Completed | 3
| T0008 | Write initial SQL tables (User, Roles, Vendor, PR, PO). | 2025-12-05 | 2025-12-05 | B.Navya | Coding | 3- Completed | 3
| T0009 | Integrate Flyway/Liquibase for DB migrations. | 2025-12-05 | 2025-12-05 | B.Navya | Coding | 3- Completed | 3
| T0010 | Test DB connection using Spring Boot. | 2025-12-05 | 2025-12-05 | B.Navya | Integration Test | 3- Completed | 3
IT2 010 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-29 | B Vaishnavi | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 2025-12-01 | 2025-12-01 | B Vaishnavi | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-02 | 2025-12-02 | B Vaishnavi | Build | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-12-04 | 2025-12-04 | B Vaishnavi | Build | 3- Completed | 1
| T0005 | ---MySQL/PostgreSQL Configuration---- | 2025-12-03 | 2025-12-03 | B Vaishnavi | Build | 3- Completed | 1
| T0006 | Install/Configure MySQL or PostgreSQL. | 2025-12-03 | 2025-12-03 | B Vaishnavi | Build | 3- Completed | 3
| T0007 | Create schema: spvms_db. | 2025-12-04 | 2025-12-04 | B Vaishnavi | Coding | 3- Completed | 3
| T0008 | Write initial SQL tables (User, Roles, Vendor, PR, PO). | 2025-12-04 | 2025-12-04 | B Vaishnavi | Coding | 3- Completed | 3
| T0009 | Integrate Flyway/Liquibase for DB migrations. | 2025-12-04 | 2025-12-04 | B Vaishnavi | Coding | 3- Completed | 3
| T0010 | Test DB connection using Spring Boot. | 2025-12-04 | 2025-12-04 | B Vaishnavi | Integration Test | 3- Completed | 3
IT3 011 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Yash Saini | Others | 1- Not Started | 0.3
| T0002 | gather requirements for framework design; |  |  | Yash Saini
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Yash Saini
| T0004 | Build vendor data models, define procurement workflows, set up APIs |  |  | Yash Saini
| T0005 | Create entities: User, Role, Vendor, Item, PR, PO. |  |  | Yash Saini
| T0006 | Establish relationships: One-to-Many, Many-to-One. |  |  | Yash Saini
| T0007 | Add JPA validation annotations. |  |  | Yash Saini
| T0008 | Configure ID generation strategies. |  |  | Yash Saini
| T0009 | Test repository queries using CommandLineRunner |  |  | Yash Saini
| T0010 |  |  |  | Yash Saini
IT3 012 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Juhee Saxena | Others | 3- Completed
| T0002 | gather requirements for framework design; |  |  | Juhee Saxena |  | 3- Completed
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Juhee Saxena |  | 3- Completed
| T0004 | Build vendor data models, define procurement workflows, set up APIs |  |  | Juhee Saxena |  | 3- Completed
| T0005 | Create entities: User, Role, Vendor, Item, PR, PO. |  |  | Juhee Saxena |  | 3- Completed
| T0006 | Create Spring Boot parent project + 4 modules (Auth, Vendor, PR, PO). |  |  | Juhee Saxena |  | 3- Completed
| T0007 | Add JPA validation annotations. |  |  | Juhee Saxena |  | 3- Completed
| T0008 | Configure ID generation strategies. |  |  | Juhee Saxena |  | 3- Completed
| T0009 | Test repository queries using CommandLineRunner |  |  | Juhee Saxena |  | 3- Completed
| T0010 |  |  |  | Juhee Saxena
IT3 013 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 |  | Others | 1- Not Started | 0.3
| T0002 | gather requirements for framework design; | [5 empty] | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | [5 empty] | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs | [5 empty] | 1
| T0005 | Create entities: User, Role, Vendor, Item, PR, PO. | [5 empty] | 1
| T0006 | Establish relationships: One-to-Many, Many-to-One. | [5 empty] | 3
| T0007 | Add JPA validation annotations. | [5 empty] | 3
| T0008 | Configure ID generation strategies. | [5 empty] | 3
| T0009 | Test repository queries using CommandLineRunner | [5 empty] | 3
| T0010 | [6 empty] | 3
IT3 014 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | K.V.DARSHINI | Others | 1- Not Started | 0.3
| T0002 | gather requirements for framework design; |  |  | K.V.DARSHINI |  |  | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | K.V.DARSHINI |  |  | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs |  |  | K.V.DARSHINI |  |  | 1
| T0005 | Create entities: User, Role, Vendor, Item, PR, PO. |  |  | K.V.DARSHINI |  |  | 1
| T0006 | Establish relationships: One-to-Many, Many-to-One. |  |  | K.V.DARSHINI |  |  | 3
| T0007 | Add JPA validation annotations. |  |  | K.V.DARSHINI |  |  | 3
| T0008 | Configure ID generation strategies. |  |  | K.V.DARSHINI |  |  | 3
| T0009 | Test repository queries using CommandLineRunner |  |  | K.V.DARSHINI |  |  | 3
| T0010 |  |  |  | K.V.DARSHINI |  |  | 3
IT3 015 | T0001 | Introduce Java tools, Spring Boot basics, and best practices;
| T0002 | gather requirements for framework design;
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle;
| T0004 | Build vendor data models, define procurement workflows, set up APIs
| T0005 | Create entities: User, Role, Vendor, Item, PR, PO.
| T0006 | Establish relationships: One-to-Many, Many-to-One.
| T0007 | Add JPA validation annotations.
| T0008 | Configure ID generation strategies.
| T0009 | Test repository queries using CommandLineRunner
IT4 016 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Sakshi Bhingare | Others | 3- Completed
| T0002 | gather requirements for framework design; | 2025-11-30 | 2025-11-30 | Sakshi Bhingare | Others | 3- Completed
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-11-30 | 2025-11-30 | Sakshi Bhingare | Build | 3- Completed
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 2025-11-30 | 2025-11-30 | Sakshi Bhingare | Build | 3- Completed
| T0005 | ---Logging & Build Automation--- | 2025-12-01 | 2025-12-01 | Sakshi Bhingare | Design | 3- Completed
| T0006 | Configure application logging (SLF4J + Logback). | 2025-12-02 | 2025-12-04 | Sakshi Bhingare | Coding | 3- Completed
| T0007 | Add log patterns for module identifiers. | 2025-12-02 | 2025-12-04 | Sakshi Bhingare | Coding | 3- Completed
| T0008 | Set up Maven build pipeline. | 2025-12-05 | 2025-12-05 | Sakshi Bhingare | Coding | 3- Completed
| T0009 | Package app as JAR and run from command. | 2025-12-05 | 2025-12-06 | Sakshi Bhingare | Coding | 3- Completed
| T0010 | Create README.md with setup instructions. | 2025-12-06 | 2025-12-07 | Sakshi Bhingare | Coding | 3- Completed
IT4 017 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Umang Joshi | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 2025-11-29 | 2025-11-29 | Umang Joshi | Others | 3- Completed | 0.3
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-11-30 | 2025-11-30 | Umang Joshi | Build | 3- Completed | 0.3
| T0004 | Build vendor data models, define procurement workflows, set up APIs | 2025-12-01 | 2025-12-01 | Umang Joshi | Build | 3- Completed | 0.3
| T0005 | ---Basic REST Controllers--- | 2025-12-02 | 2025-12-02 | Umang Joshi | Design | 3- Completed | 0.3
| T0006 | Implement sample CRUD controller (/api/test). | 2025-12-03 | 2025-12-03 | Umang Joshi | Coding | 3- Completed | 0.3
| T0007 | Expose health check API (/health). | 2025-12-03 | 2025-12-03 | Umang Joshi | Coding | 3- Completed | 0.3
| T0008 | Build a simple DTO + Mapper pattern. | 2025-12-03 | 2025-12-03 | Umang Joshi | Coding | 3- Completed | 0.3
| T0009 | Test APIs using Postman. | 2025-12-03 | 2025-12-05 | Umang Joshi | Integration Test | 3- Completed | 0.3
| T0010 | Return proper JSON responses using ResponseEntity. | 2025-12-03 | 2025-12-05 | Umang Joshi | System Test | 3- Completed | 0.3
| T0011 | Create audit table for login events. | 2025-12-09 | 2025-12-09 | Umang Joshi | Coding | 3- Completed | 1
| T0012 | Write interceptor for logging user actions. | 2025-12-10 | 2025-12-10 | Umang Joshi | Coding | 3- Completed | 2
| T0013 | Log timestamp, userId, action, requestPath. | 2025-12-11 | 2025-12-11 | Umang Joshi | Coding | 3- Completed | 2
| T0014 | Implement audit REST API for admin. | 2025-12-11 | 2025-12-12 | Umang Joshi | Coding | 3- Completed | 3
| T0015 | Export audit logs as CSV. | 2025-12-12 | 2025-12-12 | Umang Joshi | System Test | 3- Completed | 1
| T0016 | Create vendor score calculation logic. | 2025-12-15 | 2025-12-16 | Umang Joshi | Build | 3- Completed | 2
| T0017 | Add fields: delivery rate, quality rating, price score. | 2025-12-17 | 2025-12-18 | Umang Joshi | Coding | 3- Completed | 3
| T0018 | Write scheduled job to update performance scores. | 2025-12-18 | 2025-12-22 | Umang Joshi | Coding | 3- Completed | 3
| T0019 | Build API to fetch performance summary. | 2025-12-19 | 2025-12-23 | Umang Joshi | Coding | 3- Completed | 3
| T0020 | Create simple analytics query using JPQL | 2025-12-23 | 2025-12-24 | Umang Joshi | Coding | 3- Completed | 3
| T0021 | Send email on PR submission & approval. | 2025-12-29 | 2026-01-01 | Umang Joshi | Coding | 3- Completed | 4
| T0022 | Build notification templates. | 2025-12-30 | 2026-01-01 | Umang Joshi | Build | 3- Completed | 2
| T0023 | Use JavaMailSender. | 2026-01-01 | 2026-01-01 | Umang Joshi | Design | 3- Completed | 2
| T0024 | Store email logs. | 2026-01-01 | 2026-01-02 | Umang Joshi | Unit Test | 3- Completed | 4
| T0025 | Retry logic for failed emails. | 2026-01-01 | 2026-01-02 | Umang Joshi | Integration Test | 3- Completed | 4
| T0026 | Validate total cost against budgets. |  |  | Umang Joshi |  | 3- Completed
| T0027 | Log financial approvals. |  |  | Umang Joshi |  | 3- Completed
| T0028 | Secure financial data with role restrictions. |  |  | Umang Joshi |  | 3- Completed
| T0029 | Add expenditure summary table. |  |  | Umang Joshi |  | 3- Completed
| T0030 | Add cost-center mapping. |  |  | Umang Joshi |  | 3- Completed
| T0031 | Build dashboard summary API. |  |  | Umang Joshi |  | 3- Completed
| T0032 | Create KPI endpoints (cost savings, lead time). |  |  | Umang Joshi |  | 3- Completed
| T0033 | Fetch multi-module aggregated data. |  |  | Umang Joshi |  | 3- Completed
| T0034 | Cache expensive queries. |  |  | Umang Joshi |  | 3- Completed
| T0035 | Optimize using projections. |  |  | Umang Joshi |  | 3- Completed
| T0036 | Test for SQL Injection. |  |  | Umang Joshi
| T0037 | Test for broken RBAC rules. |  |  | Umang Joshi
| T0038 | Validate JWT expiration logic. |  |  | Umang Joshi
| T0039 | Implement rate limiting on sensitive endpoints. |  |  | Umang Joshi
| T0040 | Secure environment variables & config. |  |  | Umang Joshi
| T0041 | System Architecture Document. |  |  | Umang Joshi
| T0042 | API Documentation (Swagger export). |  |  | Umang Joshi
| T0043 | DB Schema Document. |  |  | Umang Joshi
| T0044 | Installation Guide. |  |  | Umang Joshi
| T0045 | User Manual (Admin, Procurement, Finance). |  |  | Umang Joshi
IT4 018 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-12-04 | 2025-12-04 | Bayagadda Sai Sharanya | Others | 3- Completed
| T0002 | gather requirements for framework design; | 2025-12-04 | 2025-12-04 | Bayagadda Sai Sharanya | Others | 3- Completed
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-12-05 | 2025-12-05 | Bayagadda Sai Sharanya | Build | 3- Completed
| T0004 | Build vendor data models, define procurement workflows, set up APIs |  |  | Bayagadda Sai Sharanya | Coding
| T0005 | ---Basic REST Controllers--- |  |  | Bayagadda Sai Sharanya | Build
| T0006 | Implement sample CRUD controller (/api/test). |  |  | Bayagadda Sai Sharanya | Build
| T0007 | Expose health check API (/health). |  |  | Bayagadda Sai Sharanya | Coding
| T0008 | Build a simple DTO + Mapper pattern. |  |  | Bayagadda Sai Sharanya | Coding
| T0009 | Test APIs using Postman. |  |  | Bayagadda Sai Sharanya | Design
| T0010 | Return proper JSON responses using ResponseEntity. |  |  | Bayagadda Sai Sharanya | Coding
IT4 019
IT4 020 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2025-11-28 | 2025-11-28 | Reshi Arasu D | Others | 3- Completed
| T0002 | gather requirements for framework design; | 2025-11-29 | 2025-11-29 | Reshi Arasu D | Others | 3- Completed
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 2025-11-30 | 2025-11-30 | Reshi Arasu D | Build | 3- Completed
| T0004 | Build vendor data models, define procurement workflows, set up APIs | 2025-12-01 | 2025-12-01 | Reshi Arasu D | Coding | 2- In Progress
| T0005 | ---Basic REST Controllers--- | 2025-12-03 | 2025-12-03 | Reshi Arasu D | Build | 3- Completed
| T0006 | Implement sample CRUD controller (/api/test). | 2025-12-05 | 2025-12-05 | Reshi Arasu D | Build | 3- Completed
| T0007 | Expose health check API (/health). | 2025-12-05 |  | Reshi Arasu D | Coding | 2- In Progress
| T0008 | Build a simple DTO + Mapper pattern. | 2025-12-05 |  | Reshi Arasu D | Coding | 1- Not Started
| T0009 | Test APIs using Postman. | 2025-12-05 |  | Reshi Arasu D | Design | 1- Not Started
| T0010 | Return proper JSON responses using ResponseEntity. | 2025-12-05 |  | Reshi Arasu D | Coding | 1- Not Started
IT5 021 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 29.11.25 | 29.11.25 | Subham Soni | Build | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 05.12.25 | 05.12.25 | Subham Soni | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 05.12.25 | 05.12.25 | Subham Soni | Build | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 05.12.25 | 05.12.25 | Subham Soni | Build | 2- In Progress | 1
| T0005 | ---Logging & Build Automation--- | 05.12.25 |  | Subham Soni | Coding | 2- In Progress | 1
| T0006 | Package app as JAR and run from command. |  |  | Subham Soni |  |  | 3
| T0007 | Add log patterns for module identifiers. |  |  | Subham Soni |  |  | 3
| T0008 | Set up Maven build pipeline. |  |  | Subham Soni |  |  | 3
| T0009 | Package app as JAR and run from command. |  |  | Subham Soni |  |  | 3
| T0010 | Create README.md with setup instructions. |  |  | Subham Soni |  |  | 3
IT5 022 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 28.11.25 | 28.11.26 | Aswini Chintala | Others | 1- Not Started | 0.3
| T0002 | gather requirements for framework design; |  |  | Aswini Chintala |  |  | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Aswini Chintala |  |  | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Aswini Chintala |  |  | 1
| T0005 | ---Logging & Build Automation--- |  |  | Aswini Chintala |  |  | 1
| T0006 | Configure application logging (SLF4J + Logback). |  |  | Aswini Chintala |  |  | 3
| T0007 | Add log patterns for module identifiers. |  |  | Aswini Chintala |  |  | 3
| T0008 | Set up Maven build pipeline. |  |  | Aswini Chintala |  |  | 3
| T0009 | Package app as JAR and run from command. |  |  | Aswini Chintala |  |  | 3
| T0010 | Create README.md with setup instructions. |  |  | Aswini Chintala |  |  | 3
IT5 023 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 2.12.25 | 2.12.25 | Arun Y | Others | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 3.12.25 | 3.12.25 | Arun Y | Build | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 5.12.25 |  | Arun Y |  |  | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Arun Y |  |  | 1
| T0005 | ---Logging & Build Automation--- |  |  | Arun Y |  |  | 1
| T0006 | Configure application logging (SLF4J + Logback). |  |  | Arun Y |  |  | 3
| T0007 | Add log patterns for module identifiers. |  |  | Arun Y |  |  | 3
| T0008 | Set up Maven build pipeline. |  |  | Arun Y |  |  | 3
| T0009 | Package app as JAR and run from command. |  |  | Arun Y |  |  | 3
| T0010 | Create README.md with setup instructions. |  |  | Arun Y |  |  | 3
IT5 024 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; | 28.11.25 | 01.12.25 | Anuj Kumar Singh |  | 3- Completed | 0.3
| T0002 | gather requirements for framework design; | 02.12.25 | 02.12.25 | Anuj Kumar Singh |  | 3- Completed | 1
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; | 04.12.25 | 05.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
| T0004 | Build vendor data models, define procurement workflows, set up APIs. | 04.12.25 | 05.12.25 | Anuj Kumar Singh |  | 3- Completed | 1
| T0005 | ---Logging & Build Automation--- | 04.12.25 | 05.12.25 | Anuj Kumar Singh |  | 3- Completed | 1
| T0006 | Configure application logging (SLF4J + Logback). | 05.12.25 | 07.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
| T0007 | Add log patterns for module identifiers. | 05.12.25 | 07.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
| T0008 | Set up Maven build pipeline. | 05.12.25 | 07.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
| T0009 | Package app as JAR and run from command. | 05.12.25 | 07.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
| T0010 | Create README.md with setup instructions. | 05.12.25 | 07.12.25 | Anuj Kumar Singh |  | 3- Completed | 3
IT5 025 | T0001 | Introduce Java tools, Spring Boot basics, and best practices; |  |  | Vani Akhila Jannavarapu
| T0002 | gather requirements for framework design; |  |  | Vani Akhila Jannavarapu
| T0003 | Tasks - Install JDK, set up database, configure Spring Boot with Maven/Gradle; |  |  | Vani Akhila Jannavarapu
| T0004 | Build vendor data models, define procurement workflows, set up APIs. |  |  | Vani Akhila Jannavarapu
| T0005 | ---Logging & Build Automation--- |  |  | Vani Akhila Jannavarapu
| T0006 | Configure application logging (SLF4J + Logback). |  |  | Vani Akhila Jannavarapu
| T0007 | Add log patterns for module identifiers. |  |  | Vani Akhila Jannavarapu
| T0008 | Set up Maven build pipeline. |  |  | Vani Akhila Jannavarapu
| T0009 | Package app as JAR and run from command. |  |  | Vani Akhila Jannavarapu
| T0010 | Create README.md with setup instructions. |  |  | Vani Akhila Jannavarapu
IT1 003 | T0001 | Implement login API (/auth/login). |  |  | Karthik Prasanna | Coding | 3- Completed
| T0002 | Create JWT token generator + validator. |  |  | Karthik Prasanna | Build | 3- Completed
| T0003 | Create authentication filter. |  |  | Karthik Prasanna | Coding | 3- Completed
| T0004 | Store hashed passwords (BCrypt). |  |  | Karthik Prasanna | Build | 3- Completed
| T0005 | Test token flow using Postman. |  |  | Karthik Prasanna | Build | 3- Completed
IT2 007 | T0001 | Implement /auth/register. |  |  | K Ganesh Kumar Rao | Coding | 3- Completed
| T0002 | Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). |  |  | K Ganesh Kumar Rao | Coding | 3- Completed
| T0003 | Create UserRole join table. |  |  | K Ganesh Kumar Rao | Coding | 2- In Progress
| T0004 | Validate user registration (email, length). |  |  | K Ganesh Kumar Rao | Coding | 2- In Progress
| T0005 | Seed default admin user. |  |  | K Ganesh Kumar Rao | Integration Test | 2- In Progress
IT2 008 | T0001 | Implement /auth/register.
| T0002 | Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR).
| T0003 | Create UserRole join table.
| T0004 | Validate user registration (email, length).
| T0005 | Seed default admin user.
IT2 009 | T0001 | Implement /auth/register. |  |  | B.Navya
| T0002 | Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). |  |  | B.Navya
| T0003 | Create UserRole join table. |  |  | B.Navya
| T0004 | Validate user registration (email, length). |  |  | B.Navya
| T0005 | Seed default admin user. |  |  | B.Navya
IT2 010 | T0001 | Implement /auth/register. | 2025-12-08 | 2025-12-08 | B Vaishnavi | Coding | 3- Completed
| T0002 | Assign roles to users (ADMIN, PROCUREMENT, FINANCE, VENDOR). | 2025-12-09 | 2025-12-09 | B Vaishnavi | Coding | 3- Completed
| T0003 | Create UserRole join table. | 2025-12-10 | 2025-12-10 | B Vaishnavi | Coding | 2- In Progress
| T0004 | Validate user registration (email, length). | 2025-12-11 | 2025-12-11 | B Vaishnavi | Coding | 2- In Progress
| T0005 | Seed default admin user. | 2025-12-12 | 2025-12-12 | B Vaishnavi | Integration Test | 2- In Progress
IT5 024 | T0001 | Integrate Swagger/OpenAPI. | 08.12.25 | 09.12.25 | Anuj Kumar Singh | Build | 3- Completed
| T0002 | Add bearer token input in Swagger UI. | 08.12.25 | 09.12.25 | Anuj Kumar Singh | Coding | 3- Completed
| T0003 | Document all authentication endpoints. | 09.12.25 | 10.12.25 | Anuj Kumar Singh | Integration Test | 3- Completed
| T0004 | Add example request/response bodies. | 09.12.25 | 10.12.25 | Anuj Kumar Singh | Coding | 3- Completed
| T0005 | Publish API documentation PDF. | 09.12.25 | 10.12.25 | Anuj Kumar Singh | Build | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
[Sprint #] | 1 | [Description of impediment or blocker] | [What was done to resolve it]
1 | 1 | Leave Plan by Team 1 | NA
1 | 1 | What Team 1 have completed Yesterday? | Introduction
1 | 1 | What Team 1 Start Doing today? | presentation
1 | 1 | Any Blocker/ Question from team 1 | Need to connect with team mates
1 | 1 | Leave Plan by Team 2 | NA
1 | 1 | What Team 2 have completed Yesterday? | Introduction
1 | 1 | What Team 2 Start Doing today? | presentation
1 | 1 | Any Blocker/ Question from team 2 | Need to connect with team mates
1 | 1 | Leave Plan by Team 3 | NA | 2025-11-29
1 | 1 | What Team 3 have completed Yesterday? | Introduction
1 | 1 | What Team 3 Start Doing today? | presentation
1 | 1 | Any Blocker/ Question from team 3 | Need to connect with team mates
1 | 1 | Leave Plan by Team 4 | NA
1 | 1 | What Team 4 have completed Yesterday? | Introduction
1 | 1 | What Team 4 Start Doing today? | presentation
1 | 1 | Any Blocker/ Question from team 4 | Need to connect with team mates
1 | 1 | Leave Plan by Team 5 | NA
1 | 1 | What Team 5 have completed Yesterday? | Introduction
1 | 1 | What Team 5 Start Doing today? | presentation
1 | 1 | Any Blocker/ Question from team 5 | Need to connect with team mates

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
0 | Sprint0 | [dd/mm/yyyy] | [dd/mm/yyyy] | [Member Name] | [What should we start doing next sprint?] | [What should we stop doing next sprint?] | [What should we continue doing?] | [Actions decided based on inputs]
1 | Sprint1 | 2025-11-28 | 2025-12-05 | Team Mentor(Chandan Kumar) | Start Story estimation Implementation | Skip redundant meetings | Daily stand-ups | Implement story-point estimation session before planning
2 | Sprint1 | 2025-11-28 | 2025-12-05 | Team 1 | presentation and practical setup | stop being silent in the class | stay consistent to the class | Try to implement what we have done in the class
3 | Sprint1 | 2025-11-28 | 2025-12-05 | Team 2 | presentation and practical setup | stop being silent in the class | attend class daily | Try to implement what we have done in the class
4 | Sprint1 | 2025-11-28 | 2025-12-05 | Team 3 | presentation and practical setup | stop being silent in the class | Stay Focused | Being more Attentive to the class
5 | Sprint1 | 2025-11-28 | 2025-12-05 | Team 4 | presentation and practical setup | stop being silent in the class | stay consistent to the class | Try to implement what we have done in the class
6 | Sprint1 | 2025-11-28 | 2025-12-05 | Team 5 | presentation and practical setup | stop being silent in the class | stay consistent to the class | Try to implement what we have done in the class
7 | Sprint4 | 2025-12-22 | 2025-12-05 | Team Mentor(Chandan Kumar)
8 | Sprint4 | 2025-12-22 | 2025-12-05 | Team 1 | presenation and pratical implemtation should be continued | stop skipping the classes | regular presentation and pratical implementation | more interactive and communication
9 | Sprint4 | 2025-12-22 | 2025-12-05 | Team 2 | Focus on Pratical work | attend daily class and stop leaving class in middle | Stay focus on pratical and presentation | more interactive class
10 | Sprint4 | 2025-12-22 | 2025-12-05 | Team 3 | Focus on Pratical work | need more contribution from team members | attend class and communicate more | more contribution from all
11 | Sprint4 | 2025-12-22 | 2025-12-05 | Team 4 | Focus on Pratical work | finish sprint in given time | implement test cases defect in excel | implemetation and updating git repo and share link in single file
12 | Sprint4 | 2025-12-22 | 2025-12-05 | Team 5 | more communication required for team 5 | dont depend on others, try yourself | supporting each other in team | Focus on Pratical work
13 | Sprint5 | 2025-12-29 | 2026-01-02 | Team 1 | Need to connect with teammates | Testing using Postman | regular presentation and pratical implementation | Implementing swagger instead of postman
14 | SPrint5 | 2025-12-29 | 2026-01-02 | Team 2 | Regularly attending the classes | Testing using Postman | complete work on time | implement token based auth as team1
15 | SPrint5 | 2025-12-29 | 2026-01-02 | Team 3 | Need to connect with teammates | Not to leave the class in the middle | complete the sprint on time | Connect with teammate and complete the work
16 | Sprint5 | 2025-12-29 | 2026-01-02 | Team 4 | Be active and implement practical work | do not attend the meeting for attendance | complete the sprint on time | implementing code review
17 | Sprint5 | 2025-12-29 | 2026-01-02 | Team 5 | absent | absent | absent | absent